## Master Daily Stand-up
ENGLABS MASTER DAILY STAND-UP PROJECT REPORT
Date: Friday, 19 June, 2026
Sr. No | Quote ID | Project Value (INR) | Client | Finish / Part Details | PO Qty | PO Date | PO Received | Inputs Required | Englabs Assigned Staff | Production Planning | Quality Check | Supervision | Daily Status / Discussing Notes | Preparing Parts Info Date | Porter Handling Staff | Porter Service | Route | Porter Cost (INR) | Sent Qty | Balance Qty | Project Status | Customer Payment | Vendor Payment
1 | C5230 | 21500 | Menthosa | — | — | — | NO | NO | Anurag | — | — | Gaurav Sir | Project Closed According to Anurag | 17-06-2026 | Person | yes | SKTECHNO MOHALI -> Englabs -> PU MENTHOSA | — | — | — | Closed | ADVANCE DONE | —
2 | C5251 | 66920 | ITL (SONALIKA) | MJF Black Paint | 32 | 05-06-2026 | NO | NO | Shubham | Anurag | Anurag | Gaurav Sir | — | — | Shubham | — | — | — | 0 | 32 | Released | — | —
3 | C5254 | 374716 | ITL (SONALIKA) | MJF Black Paint | 36 | 06-06-2026 | NO | NO | Shubham | Anurag | Anurag | Gaurav Sir | — | — | Shubham | — | — | — | 0 | 36 | Released | — | —
4 | C5262 | 14840 | ITL (SONALIKA) | MJF Orange Paint | 4 | 06-06-2026 | YES | NO | Shubham | Anurag | Anurag | Gaurav Sir | — | — | Shubham / Anurag | — | — | — | 0 | 4 | Released | — | —
5 | C5273 | 128352 | ITL (SONALIKA) | MJF Black Paint | 48 | 12-06-2026 | NO | NO | Anurag | Anurag | Anurag | Gaurav Sir | — | 24-06-2026 | Anurag | — | — | — | 0 | 48 | Released | — | —
6 | C5286 | — | ITL (SONALIKA) | MJF Painted | 10 | — | NO | NO | Devanshu | Anurag | Anurag | Gaurav Sir | — | — | Devanshu | — | Noida -> Englabs -> Hoshiarpur | — | 0 | 10 | Released | — | —
7 | C5280 | 103425 | ITL (SONALIKA) | VC Rubber | 15 | — | NO | NO | Anurag | — | Devanshu | Gaurav Sir | — | Not Confirm | Anurag | — | Noida -> Englabs -> Hoshiarpur | — | 0 | 15 | Released | — | —
8 | C5267 | 104180 | ITL (SONALIKA) | VC Rubber | 14 | 13-06-2026 | NO | NO | Devanshu | — | Anurag | Gaurav Sir | — | 23-06-2026 | Devanshu | — | Noida -> Englabs -> Hoshiarpur | — | 0 | 14 | Released | — | —
9 | C5232 | 29766 | ITL (SONALIKA) | MJF Black Paint | 5 | 12-06-2026 | NO | NO | Devanshu | Anurag | Anurag | Gaurav Sir | This part is currently with staff member Devanshu; it still needs to be painted, and only then can it be sent to the client. | Painting Under Processing Englabs | Devanshu | hold | Delhi -> Englabs -> Hoshiarpur | 168 | 5 | 0 | Under Process | — | —
10 | C5231 | 17220 | ITL (SONALIKA) | MJF Black Paint | 2 | 12-06-2026 | NO | NO | Devanshu | Anurag | Anurag | Gaurav Sir | — | Painting Under Processing Englabs | Devanshu | hold | Delhi -> Englabs -> Hoshiarpur | 168 | 2 | 0 | Under Process | — | —
11 | C5152 | 21260 | BCH Electric Limited | SLS Raw | 8 | 15-06-2026 | YES | NO | Devanshu | — | Devanshu | Gaurav Sir | Devanshu & Shubham to Rohit | 22-06-2026 | Devanshu | NO | Noida -> Faridabad -> NIL | — | 0 | 8 | Released | — | —
12 | C5288 | 21072 | Orient | SLS ABS / Nylon GF Black Paint | 11 | 10-06-2026 | NO | NO | Devanshu | — | Devanshu | Gaurav Sir | Under Process Porter Service | 18-06-2026 | Devanshu | NO | Ghaziabad -> Faridabad -> NIL | 450 | 11 | 0 | Closed | — | —
13 | C5023 | 41320 | AV MACHINING | VC P.P. Inserts (Vacuum Casting) | 90 | 23-05-2026 | NO | NO | Devanshu | — | — | Gaurav Sir | Vacuum Casting @Ramesh ¦ Shubham to Rohit | 20-06-2026 | Devanshu | NO | Noida -> pune -> NIL | — | 0 | 90 | Released | — | Bharat sir
14 | New Project | — | AV MACHINING | Rapid Proto Info Pending | — | — | NO | NO | Shubham | — | — | Gaurav Sir | Developed at Rapid proto preparing part information by 21-06-2026 | 22-06-2026 | Shubham | NO | chennai -> Englabs -> pune | — | — | — | New Project | — | Bharat sir
15 | C5285 | 34150 | AUTO DYNAMICS | Nylon GF Black Paint | 5 | 17-06-2026 | NO | NO | Shubham | Anurag | Anurag | Gaurav Sir | Talekar cross check shubham | 22-06-2026 | Shubham | NO | pune -> Englabs -> pune | — | 0 | 5 | Released | — | 20% advance
16 | C5283 | 219500 | AUTO DYNAMICS | Nylon GF Black Paint | 9 | 17-06-2026 | NO | NO | Shubham | Anurag | Anurag | Gaurav Sir | Talekar cross check shubham | 22-06-2026 | Shubham | — | — | — | 0 | 9 | Released | — | —
17 | C5239 | 33650 | SARK INDUSTRIES | Scanning & Modelling | 5 | 26-05-2026 | NO | NO | Shubham | — | — | Gaurav Sir | design only | 20-06-2026 | Shubham | NO | nil -> nil -> nil | — | 0 | 5 | Released | — | Bharat sir
18 | C5195 | 110100 | Labat Asia | VC ABS Grey Paint | 150 | 05-05-2026 | YES | NO | Shubham | Shubham & Anurag | Anurag(VQ) | Gaurav Sir | — | — | Shubham | — | — | — | 141 | 9 | Released | — | —
19 | C5230 | 25430 | Enertics | NYLON GF | 1000 | — | NO | Part Feed Back | Anurag | — | Anurag | Gaurav Sir | 1,000 pieces are arriving today, and the target is to dispatch them today itself! Anurag will handle this. | Porter Time 11:30am | Anurag | YES | Chandigarh -> Englabs -> Mohali | 0 | 60 | 940 | Under Process | — | —
20 | C5248 | 155950 | BAJAJ | MS M/C | 10 | 08-06-2026 | NO | Cad File | Devanshu | — | Anurag | Gaurav Sir | — | — | Devanshu | — | Talekar pune -> mumbai -> NIL | — | 0 | 10 | Released | 30 days | —
21 | C5283 | 215000 | AUTO DYNAMICS | Nylon GF Black Paint (Alternate Quote) | — | — | NO | NO | Shubham | Anurag | Anurag | Gaurav Sir | Cross-check details | — | Shubham | — | — | — | — | — | Released | — | —
22 | C5285 | 140000 | AUTO DYNAMICS | Nylon GF Black Paint (Alternate Quote) | — | — | NO | NO | Shubham | Anurag | Anurag | Gaurav Sir | Cross-check details | — | Shubham | — | — | — | — | — | Released | — | —
23 | C5233 | — | Labat Asia | ABS Black (Top Plate) | 55 | — | YES | NO | Anurag | Anurag | Anurag | Gaurav Sir | Active production dispatches in progress | — | — | — | — | — | 15 | 40 | Released | — | —
24 | C5233 | — | Labat Asia | ABS Silver (Bottom Plate) | 55 | — | YES | NO | Anurag | Anurag | Anurag | Gaurav Sir | Active production dispatches in progress | — | — | — | — | — | 40 | 15 | Released | — | —
25 | — | — | Labat Asia | ABS Black (Top Plate) | 125 | — | — | NO | Anurag | Anurag | Anurag | Gaurav Sir | Release pending from client | — | — | — | — | — | 0 | 125 | Order yet to release | — | —
26 | — | — | Labat Asia | ABS Silver (Bottom Plate) | 125 | — | — | NO | Anurag | Anurag | Anurag | Gaurav Sir | Release pending from client | — | — | — | — | — | 0 | 125 | Order yet to release | — | —
27 | — | — | Labat Asia | Al Silver Paint (3 Pin) | 100 | — | — | NO | Anurag | Anurag | Anurag | Gaurav Sir | Release pending from client | — | — | — | — | — | 0 | 100 | Order yet to release | — | —
28 | — | — | Labat Asia | Al Silver Paint (Multi Pin) | 100 | — | — | NO | Anurag | Anurag | Anurag | Gaurav Sir | Release pending from client | — | — | — | — | — | 0 | 100 | Order yet to release | — | —