## Operations
Client | Project ID | Finish | PO Qty | Date | Client Date | Dispatched Qty | Pending Qty | Status | QC | Vendor | Expected Date | Supervisor | Remarks | Date of Standup | Material | Comments | PO | Payment Status | Actual Dispatch Date | PO Dispatch Date | From City | To Eng Labs | To City | Feedback from customer
Labat Asia | C1595 | VC; ABS; Grey Painting | 150 | 2026-05-05 |  | 93 | 57 | Excel |  |  |  | Dispatch by Anurag; 14-05-2026 |  | 2026-06-01 | Plastic | Ready by Monday and dispatch
ITL | C5204 |  |  | 2026-05-09 |  | 0 | 5 |  |  |  |  | QC Done; | PO | 2026-06-01 | Plastic | Followed up but there are some changes pending;
EndureAir | C5229 | PA12=30; TPV = 40; PETG = 40 | 110 | 2026-05-26 |  | 0 | 110 | Will Print |  |  |  | Adroitec |  | 2026-06-01 | Plastic | Will have to float to Rapid Proto; Check with Bharat if these need to be given to Pune Marco Polo as they have capacity
AV Machining | C5023 |  | 135 | 2026-05-07 |  | 63 | 72 | Excel |  |  |  | Anurag 18/05 26/05 | Anurag | 2026-06-01 | Plastic
Baaz Bikes | C5243 | SUA ABS | 17 | 2026-05-29 |  | 0 | 17 | Will Print | [5 empty] | 2026-06-01 | Plastic
SARK | C5230 | Scanning Modelling | 5 | 2026-05-26 |  | 0 | 5 | Will Scan |  |  |  | Anurag | FCS 16/05/2026 | 2026-06-01 | Plastic
Hella | C5026 | MJF | 5 | 2026-05-27 |  | 0 | 5 | Will Print |  |  |  | PlastiPack |  | 2026-06-01 | Plastic
Hella | C5215 | MJF | 4 | 2026-05-16 |  | 0 | 4 | Will Print |  |  |  | 23/5 PlastiPack | PU Shubham | 2026-06-01 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Will Manufacture |  |  |  | Excel |  | 2026-06-01 | Plastic
Uno Minda | C5190 | Metal = 11+11; ABS = 1+1 | 24 | 2026-05-08 |  | 0 | 24 | Will Manufacture |  |  |  | Telakar |  | 2026-06-01 | Metal
Henkel | C5223 | Nylon; GF | 10 | 2026-05-19 |  | 2 | 8 | Will Manufacture |  |  |  | Talekar; 11 |  | 2026-06-01 | Metal
Enertics | C5230 | [6 empty] | In Process | [5 empty] | 2026-06-01 | Metal
Vibracoustic | C5224 | Machining 6063 T6 | 18 | 2026-05-28 |  | 0 | 18 | Will Manufacture |  |  |  | Sanjeev 28/05/2026 |  | 2026-06-01 | Metal
Yash Appliances | C5247 | SLA; Painting | 10 | 2026-06-01 |  | 0 | 10 |  |  |  |  | WorkAad; 06-06-2026 |  | 2026-06-02 | Plastic
Labat Asia | C1595 | VC; ABS; Grey Painting | 150 | 2026-05-05 |  | 93 | 57 | Paint is pending; will be done tomorrow |  |  |  | Dispatch by Anurag; 14-05-2026 |  | 2026-06-02 | Plastic
ITL | C5204 |  |  | 2026-05-09 |  | 0 | 5 | Packed; Waiting for PO |  |  |  | QC Done; | PO | 2026-06-02 | Plastic
EndureAir | C5229 | PA12=30; TPV = 40; PETG = 40 | 110 | 2026-05-26 |  | 0 | 110 | Courier will be sent today Visual QC was done and photos shared on the group |  |  |  | Adroitec |  | 2026-06-02 | Plastic
AV Machining | C5023 |  | 135 | 2026-05-07 |  | 63 | 72 | Expected today |  |  |  | Anurag 18/05 26/05 | Anurag | 2026-06-02 | Plastic
Baaz Bikes | C5243 | SUA ABS | 17 | 2026-05-29 |  | 0 | 17 | Parts are ready by WorkAd Visual QC will be done and then sent mostly by tomorrow | [5 empty] | 2026-06-02 | Plastic
SARK | C5230 | Scanning Modelling | 5 | 2026-05-26 |  | 0 | 5 | PPT will be sent by them around 11 am; Checking file is needed |  |  |  | Anurag | FCS 16/05/2026 | 2026-06-02 | Plastic
Hella | C5026 | MJF | 5 | 2026-05-27 |  | 0 | 5 | Plastipak is working on this; Expected to reach today |  |  |  | PlastiPack |  | 2026-06-02 | Plastic
Hella | C5215 | MJF | 4 | 2026-05-16 |  | 0 | 4 | Ready and waiting for the PO to dispatch |  |  |  | 23/5 PlastiPack | PU Shubham | 2026-06-02 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Parts expected on June 5th and will be sent from Noida; Visual QC will be done |  |  |  | Excel |  | 2026-06-02 | Plastic
Uno Minda | C5190 | Metal = 11+11; ABS = 1+1 | 24 | 2026-05-08 |  | 0 | 24 | Packed but waiting for the PO |  |  |  | Telakar |  | 2026-06-02 | Metal
Henkel | C5223 | Nylon; GF | 10 | 2026-05-19 |  | 2 | 8 | Friday; Visual QC and Dispatch |  |  |  | Talekar; 11 |  | 2026-06-02 | Metal
Enertics | C5230 | [6 empty] | Ongoing; Waiting for mould changes and PO; Trial part will be sent today; Expected by end of the week | [5 empty] | 2026-06-02 | Metal
Vibracoustic | C5224 | Machining 6063 T6 | 18 | 2026-05-28 |  | 0 | 18 | Done on Saturday; |  |  |  | Sanjeev 28/05/2026 |  | 2026-06-02 | Metal
EndureAir | C5242 | MJF | 2 | 2026-06-01 |  | 0 | 2 | Vendor will make by Wednesday; Dispatch after that |  |  |  | Adroitec; Shubham |  | 2026-06-06 | Plastic
Sonalika | C5251 | MJF | 32 | 2026-06-05 |  | 0 | 32 | Will be ready by Wed and we will get by Thursday; |  |  |  | Rapid Proto; Shubham |  | 2026-06-06 | Plastic
Sonalika | C5254 | MJF | 36 | 2026-06-06 |  | 0 | 36 | Will be ready by Friday and dispatched by Monday |  |  |  | Rapid Proto; Shubham |  | 2026-06-06 | Plastic
Sonalika | C5262 | MJF | 4 | 2026-06-06 |  | 0 | 4 | Will be ready by Friday and dispatched by Monday |  |  |  | Rapid Proto; Shubham |  | 2026-06-06 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been finalised by Bharat |  |  |  | CICU; Shubham |  | 2026-06-06 | Scanning
Param Appliances | C5249 | MJF | 2 | 2026-06-04 |  | 0 | 2 | Tuesday; We will get by Wednesday |  |  |  | Adroitec; Anurag |  | 2026-06-06 | Plastic
Aebocode | C5252 | MJF | 1 | 2026-06-04 |  | 0 | 1 | Tuesday; We will get by Wednesday |  |  |  | Adroitec; Anurag |  | 2026-06-06 | Plastic
EndureAir | C5242 | MJF - PA12 | 2 | 2026-06-01 |  | 0 | 2 | Vendor will make by Wednesday; Dispatch after that |  |  |  | Adroitec; Shubham |  | 2026-06-11 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Will be ready by Wed and we will get by Thursday; |  |  |  | Rapid Proto; Shubham |  | 2026-06-11 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | Will be ready by Friday and dispatched by Monday |  |  |  | Rapid Proto; Shubham |  | 2026-06-11 | Plastic
Sonalika | C5262 | MJF Black Paint | 4 | 2026-06-06 |  | 0 | 4 | Will be ready by Friday and dispatched by Monday |  |  |  | Rapid Proto; Shubham |  | 2026-06-11 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been finalised |  |  |  | CICU; Shubham |  | 2026-06-11 | Scanning
Param Appliances | C5249 | MJF | 2 | 2026-06-04 |  | 0 | 2 | Tuesday; We will get by Wednesday |  |  |  | Adroitec; Anurag |  | 2026-06-11 | Plastic
Aebocode | C5252 | MJF | 1 | 2026-06-04 |  | 0 | 1 | Tuesday; We will get by Wednesday |  |  |  | Adroitec; Anurag |  | 2026-06-11 | Plastic
Labat Asia | C5195 | VC, ABS, Grey Printing | 150 | 2026-05-05 |  | 93 | 57 |  |  |  |  | Excel |  | 2026-06-11 | Plastic
Sonalika | C5204 | MJF Black Paint | 5 | 2026-05-09 |  | 0 | 5 | QC Done |  |  |  | Anurag |  | 2026-06-11 | Plastic
Microtek | C5260 | MJF | 4 | 2026-06-11 |  | 0 | 4 | Will Print | [5 empty] | 2026-06-11 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Will Manufacture | [5 empty] | 2026-06-11 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will Mnufacture | [5 empty] | 2026-06-11 | Metal
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Will Manufacture | [5 empty] | 2026-06-11 | Metal
Enertics | C5230 | [12 empty] | 2026-06-11 | Metal
Labat Asia | C5195 | VC ABS Grey Printing | 150 | 2026-05-05 |  | 93 | 57 | Excel |  |  |  | Dispatch by 14-06-2026 |  | 2026-06-16 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Will be ready for dispatch by next Tuesday |  |  |  | Rapid Proto; Shubham |  | 2026-06-16 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | Will be ready for dispatch by next Tuesday |  |  |  | PlastiPack; Shubham |  | 2026-06-16 | Plastic
Sonalika | C5262 | MJF Black Paint | 4 | 2026-06-06 |  | 0 | 4 | Will be ready for dispatch by next Tuesday |  |  |  | Excel; Shubham |  | 2026-06-16 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been sent; Payment is pending |  |  |  | CICU; Shubham |  | 2026-06-16 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Will Manufacture; Will get completed by June 20 |  |  |  | Excel; Shubham |  | 2026-06-16 | Plastic
HC Robotics | C5273 | MJF | 48 | 2026-06-12 |  | 0 | 48 | Will Print | [5 empty] | 2026-06-16 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Will Print | [5 empty] | 2026-06-16 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Will Print | [5 empty] | 2026-06-16 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent today during the day | [5 empty] | 2026-06-16 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will Mnufacture | [5 empty] | 2026-06-16 | Metal
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Will Manufacture | [5 empty] | 2026-06-16 | Metal
Enertics | C5230 | [12 empty] | 2026-06-16 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Will Manufacture | [5 empty] | 2026-06-16 | Plastic
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Will Manufacture |  |  |  | idemi |  | 2026-06-16 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture |  |  |  | excel |  | 2026-06-16 | Plastic
Sonalika | C5267 | VC | 4 | 2026-06-12 |  | 0 | 4 | Will Manufacture |  |  |  | excel |  | 2026-06-16 | Plastic
Labat Asia | C5195 | VC ABS Grey Printing | 150 | 2026-05-05 |  | 93 | 57 | Still in Painting stage; got the parts yesterday; QC was done; Inserting for the components needs to be done by Arjun tomorrow; Dispatch will be done on Saturday (20th June) | Needs to be done by Anurag | Excel | 2026-06-20 | Shubham |  | 2026-06-18 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Joining stage; 28 parts are in primaring stage and 4 (bigger parts) in joining stage; No PO has come yet | Needs to be done by Anurag | Rapid Proto; | 2026-06-23 | Anurag |  | 2026-06-18 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | Will be ready for dispatch by next Tuesday; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-18 | Plastic
Sonalika | C5262 | MJF Black Paint | 4 | 2026-06-06 |  | 0 | 4 | Received the parts but inserting needs to be done; Arjun's bandwidth is needed so we will have to wait till Saturday | Needs to be done by Anurag | Excel; | 2026-06-20 | Shubham |  | 2026-06-18 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been sent; Payment is pending ; Client will come to the office on Monday to share the feedback; Bharat will have to be in the office; Shubham needs to debrief Bharat |  | CICU; |  | Shubham |  | 2026-06-18 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Will get completed by tomorrow; Aruti to check the previous QC Sheets that Excel has sent; 40 delivered; 50 have not been delivered; Shubham to ensure packaging is good | QC will be done on video call; | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-18 | Plastic
HC Robotics | C5273 | MJF | 48 | 2026-06-12 |  | 0 | 48 | Will Print; Will be delivered to us by Monday; Painting load overall next week will be very high so 5-6 days buffer to be kept for painting | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-18 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Ready at Excel; receive today by evening; No PO | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-18 | Plastic | Painting on Sunday
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Ready at Excel; receive today by evening; No PO | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-18 | Plastic | Painting on Sunday
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-18 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will Mnufacture; 3D Data is still pending from the client; No PO | Shubham | Talekar |  | Shubham |  | 2026-06-18 | Metal
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | Talekar |  | Shubham |  | 2026-06-18 | Metal
Enertics | C5230 | [6 empty] | 700-800 components; Salil discuss with Bharat |  |  |  | Anurag |  | 2026-06-18 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO; Payment will have to be tracked | Shubham | SK Techno |  | Shubham |  | 2026-06-18 | Plastic
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Sent tomorrow from the vendor; Painting to be ready by Wed | Anurag | idemi | 2026-06-24 | Shubham |  | 2026-06-18 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture; Will be ready by 25th June and sent to Englabs by next Friday; No PO | Anurag | excel Rapid Tech |  | Devyanshu |  | 2026-06-18 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will Manufacture; Will be ready by 25th June and sent to Englabs by 26th June; No PO | Anurag | excel Rapid Tech |  | Devyanshu |  | 2026-06-18 | Plastic
AutoDyanamics | C5283 | Machining | 6 | 2026-06-17 |  | 0 | 6 | Will Manufacture; Go ahead given to the vendor; PO awaited | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-18 | Metal
AutoDyanamics | C5285 | Machining | 9 | 2026-06-17 |  | 0 | 9 | Will Manufacture; Go ahead given to the vendor; PO awaited | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-18 | Metal
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture | Anurag | Rapid Proto; | Expected 23-06-2026 | Shubham |  | 2026-06-18 | Plastic
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Will Print | Anurag | Rapid Proto; | Expected 25-06-2026 | Shubham |  | 2026-06-18 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Will get on Monday | Devanshu | Adroitec | Expected 22-06-2026 | Devanshu |  | 2026-06-18 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-18 | Plastic
Labat Asia | C5195 | VC ABS Grey Printing | 150 | 2026-05-05 |  | 93 | 57 | Inserting for the components needs to be done by Arjun today; Dispatch will be done after the payment; Expected Monday or Tuesday; Anurag will have to oversee | Needs to be done by Anurag | Excel | 2026-06-22 | Shubham/Anurag |  | 2026-06-20 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Painting is in progress; Will get completed by Tuesday; No PO has come yet | Needs to be done by Anurag | Rapid Proto; | 2026-06-23 | Anurag |  | 2026-06-20 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | Will be ready for dispatch from the vendor by next Tuesday; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-20 | Plastic
Sonalika | C5262 | MJF Black Paint | 14 | 2026-06-06 |  | 0 | 14 | Will be sent by vendor around 25-06-2026; Visual QC | Needs to be done by Anurag | Excel; | 2026-06-26 | Shubham |  | 2026-06-20 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been sent; Payment is pending ; Client will come to the office on Monday to share the feedback; Bharat will have to be in the office; Shubham needs to debrief Bharat |  | CICU; |  | Shubham |  | 2026-06-20 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Completed; QC done visually; Packaging checked by Shubham; Tuesday feedback | Done | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-20 | Plastic
HC Robotics | C5273 | MJF | 48 | 2026-06-12 |  | 0 | 48 | Will Print; Will be delivered to us by Wednesday; Painting load overall next week will be very high so 5-6 days buffer to be kept for painting | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-20 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Painting in progress; Will be sent today; | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-20 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Painting in progress; Will be sent today; | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-20 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken next week; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-20 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will be sent to us by vendor on Tuesday; QC will be done by Anurag and needs to be sent on Tuesday | Shubham | SK Techno | 2026-06-23 | Shubham |  | 2026-06-20 | Metal
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | ` |  | Shubham |  | 2026-06-20 | Metal
Enertics | C5230 | [6 empty] | 700-800 components; Salil discuss with Bharat |  |  |  | Anurag |  | 2026-06-20 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO is needed; Payment done | Shubham | SK Techno |  | Shubham |  | 2026-06-20 | Plastic
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Delayed by Courier; Will come on Monday; Painting to be ready by Wed; No PO | Anurag | idemi | 2026-06-24 | Shubham |  | 2026-06-20 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture; Will be ready by 25th June and sent to Englabs by next Friday; No PO | Anurag | excel Rapid Tech |  | Devyanshu |  | 2026-06-20 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will Manufacture; Will be ready by 25th June and sent to Englabs by 26th June; No PO | Anurag | excel Rapid Tech |  | Devyanshu |  | 2026-06-20 | Plastic
AutoDyanamics | C5283 | Machining | 6 | 2026-06-17 |  | 0 | 6 | Will Manufacture; Go ahead given to the vendor; Will be sent by Talekar on Monday; Painting has to be done | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-20 | Metal
AutoDyanamics | C5285 | Machining | 9 | 2026-06-17 |  | 0 | 9 | Will Manufacture; Go ahead given to the vendor; Will be sent by Talekar on Monday; Painting has to be done | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-20 | Metal
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture; Expected from vendor by Wednesday | Anurag | Rapid Proto; | Expected 23-06-2026 | Shubham |  | 2026-06-20 | Plastic
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Will Print; Will be dispatched from Rapid Proto on Sunday | Anurag | Rapid Proto; | Expected 25-06-2026 | Shubham |  | 2026-06-20 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Delivered; QC was done by Rohit; Feedback will be taken by Rohit | Devanshu | Adroitec | Expected 22-06-2026 | Devanshu |  | 2026-06-20 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today; QC was done by Rohit; Feedback will be taken by Rohit | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-20 | Plastic
Aebocode | C5296 | MJF | 14 | 2026-06-19 |  | 0 | 14 | Will be delivered for QC on Monday and needs to be sent to the customer | Anurag | Excel | 2026-06-25 | Devanshu |  | 2026-06-20 | Plastic
Labat Asia | C5195 | VC ABS Grey Printing | 150 | 2026-05-05 |  | 93 | 57 | It is not urgent as per the customer so kept on hold; Inserting is pending which will be done by Arjun after other projects are completed | Needs to be done by Anurag | Excel | Delayed as per conversation with the customer | Shubham/Anurag |  | 2026-06-22 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Painting is in progress; Will get completed by Friday; Target of Tuesday given to staff; No PO has come yet | Needs to be done by Anurag | Rapid Proto; | 2026-06-27 | Anurag |  | 2026-06-22 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | Will be ready for dispatch from the vendor by next Tuesday; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-22 | Plastic
Sonalika | C5262 | MJF Black Paint | 14 | 2026-06-06 |  | 0 | 14 | Will be sent by vendor around 25-06-2026; Visual QC | Needs to be done by Anurag | Excel; | 2026-06-26 | Shubham |  | 2026-06-22 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been sent; Payment is pending ; Client will come to the office on Monday to share the feedback; Bharat will have to be in the office; Shubham needs to debrief Bharat |  | CICU; |  | Shubham |  | 2026-06-22 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Completed; QC done visually; Packaging checked by Shubham; Tuesday feedback | Done | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-22 | Plastic
HC Robotics | C5273 | MJF | 64 | 2026-06-12 |  | 0 | 64 | Some parts will come tomorrow and some by Wednesday; | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-22 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Dispatched to customer; Feedback on Tuesday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-22 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Dispatched to customer; Feedback on Tuesday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-22 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken next week; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-22 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will be sent to us by vendor on Tuesday; QC will be done by Anurag and needs to be sent on Tuesday | Shubham | SK Techno | 2026-06-23 | Shubham |  | 2026-06-22 | Metal
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | SK Techno |  | Shubham |  | 2026-06-22 | Metal
Enertics | C5230 | [6 empty] | 300 sets will be delivered today; 450 lower parts pending and 320 upper parts pending; target date tomorrow; Some lower parts around 200 are rejected |  | PlastoFur | 2026-06-24 | Anurag |  | 2026-06-22 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO is needed; Payment done | Shubham | SK Techno |  | Shubham |  | 2026-06-22 | Plastic
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Delayed by Courier; Will come on Monday; Painting to be ready by Wed; No PO | Anurag | idemi | 2026-06-24 | Shubham |  | 2026-06-22 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture; Will be ready by 25th June and sent to Englabs by next Friday; No PO | Anurag | excel Rapid Tech |  | Devyanshu |  | 2026-06-22 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will Manufacture; Will be ready by 25th June and sent to Englabs by 26th June; No PO | Anurag | excel Rapid Tech |  | Devyanshu |  | 2026-06-22 | Plastic
AutoDyanamics | C5283 | Machining | 6 | 2026-06-17 |  | 0 | 6 | Will Manufacture; Go ahead given to the vendor; Will be sent by Talekar on Monday; Painting has to be done | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-22 | Metal
AutoDyanamics | C5285 | Machining | 9 | 2026-06-17 |  | 0 | 9 | Will Manufacture; Go ahead given to the vendor; Will be sent by Talekar on Monday; Painting has to be done | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-22 | Metal
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture; Expected from vendor by Wednesday | Anurag | Rapid Proto; | Expected 23-06-2026 | Shubham |  | 2026-06-22 | Plastic
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Will Print; Will be dispatched from Rapid Proto on Sunday | Anurag | Rapid Proto; | Expected 25-06-2026 | Shubham |  | 2026-06-22 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Delivered; QC was done by Rohit; Feedback will be taken by Rohit | Devanshu | Adroitec | Expected 22-06-2026 | Devanshu |  | 2026-06-22 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today; QC was done by Rohit; Feedback will be taken by Rohit | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-22 | Plastic
Aebocode | C5296 | MJF | 14 | 2026-06-19 |  | 0 | 14 | Will be delivered for QC on Monday and needs to be sent to the customer | Anurag | Adroitec | 2026-06-25 | Devanshu |  | 2026-06-22 | Plastic
HC Robotics | C5295 | MJF/PA12 NYLON/Aircraft grey or Black outside only | 4 | 2026-06-22 | ASAP | 0 | 4 | PO from the vendor has come today; Should come to EngLabs by Friday; Painting should happen on Saturday | Devanshu | Adroitec | 2026-06-29 | Devanshu |  | 2026-06-22 | Plastic
Bajaj | C5264 | MJF+SLA; Glass Filled, Transparent | 73 | 2026-06-23 | ASAP | 0 | 73 | Vendor has not been flinalised yet | Devanshu | TBD | 2026-06-29 | Devanshu |  | 2026-06-23 | Plastic
Bajaj | C5255 | VC Rubber | 20 | 23-06-2026 |  | 0 | 20 | Will start manufacturing | Devanshu | Excel | 2026-07-02 | Devanshu |  | 2026-06-23 | Plastic
Labat Asia | C5195 | VC ABS Grey Painting | 150 | 2026-05-05 |  | 93 | 57 | It is not urgent as per the customer so kept on hold; Inserting is pending which will be done by Arjun after other projects are completed | Needs to be done by Anurag | Excel | Delayed as per conversation with the customer | Shubham/Anurag |  | 2026-06-23 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Painting is in progress; Will get completed by Friday; Target of Tuesday given to staff; No PO has come yet | Needs to be done by Anurag | Rapid Proto; | 2026-06-27 | Anurag |  | 2026-06-23 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | Will be ready for dispatch from the vendor tomorrow; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-23 | Plastic
Sonalika | C5262 | MJF Black Paint | 14 | 2026-06-06 |  | 0 | 14 | Will be sent by vendor around 25-06-2026; Visual QC | Needs to be done by Anurag | Excel; | 2026-06-26 | Shubham |  | 2026-06-23 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been sent; Payment is pending; Bharat will have to be in the office; Shubham needs to debrief Bharat; Zoom meeting has to be done ; Meeting still pending |  | CICU; |  | Shubham |  | 2026-06-23 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Completed; QC done visually; Packaging checked by Shubham; Wednesday feedback | Done | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-23 | Plastic
HC Robotics | C5273 | MJF | 64 | 2026-06-12 |  | 0 | 64 | Some parts will come tomorrow and some by Wednesday; | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-23 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Dispatched to customer; Feedback on Wed | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-23 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Dispatched to customer; Feedback on Wed | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-23 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken next week; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-23 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will be sent to us by vendor on Tuesday; QC will be done by Anurag and needs to be sent on Wed | Shubham | SK Techno | 2026-06-24 | Shubham |  | 2026-06-23 | Metal
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | SK Techno |  | Shubham |  | 2026-06-23 | Metal
Enertics | C5230 | [6 empty] | 320 pending; will be dispatched tomorrow |  | PlastoFur | 2026-06-24 | Anurag |  | 2026-06-23 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO is needed; Payment done | Shubham | SK Techno |  | Shubham |  | 2026-06-23 | Plastic
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Delayed by Courier; Will come on Monday; Painting to be ready by Fri; No PO | Anurag | idemi | 2026-06-27 | Shubham |  | 2026-06-23 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture; Will be ready by 25th June and sent to Englabs by next Saturday; No PO | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-23 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will Manufacture; Will be ready by 25th June and sent to Englabs by Saturday; No PO | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-23 | Plastic
AutoDyanamics | C5283 | Machining | 8 (split parts) | 2026-06-17 |  | 0 | 6 | Parts will come tomorrow from Talekar; Joining and painting will have to be done; | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-23 | Metal
AutoDyanamics | C5285 | Machining | 15 (split parts) | 2026-06-17 |  | 0 | 9 | Parts will come tomorrow from Talekar; Joining and painting will have to be done; | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-23 | Metal
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture; Expected from vendor by Wednesday | Anurag | Rapid Proto; | Expected 23-06-2026 | Shubham |  | 2026-06-23 | Plastic
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Reached EngLabs; Joinig will start after Sonalika; Delayed | Anurag | Rapid Proto; | Expected 27-06-2026 | Shubham |  | 2026-06-23 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Delivered; QC was done by Rohit; Feedback will be taken by Rohit | Devanshu | Adroitec | Expected 22-06-2026 | Devanshu |  | 2026-06-23 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today; QC was done by Rohit; Feedback will be taken by Rohit | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-23 | Plastic
Aebocode | C5296 | MJF | 14 | 2026-06-19 |  | 0 | 14 | Will be delivered for QC on Friday and needs to be sent to the customer | Anurag | Adroitec | 2026-06-27 | Devanshu |  | 2026-06-23 | Plastic
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Joining has started; Need more resources to complete this | Anurag | Rapid Proto; | Expected 27-06-2026 | Shubham |  | 2026-06-24 | Plastic
Aebocode | C5296 | MJF | 14 | 2026-06-19 |  | 0 | 14 | All have reached EngLabs; QC will be done and be sent today | Anurag | Adroitec | 2026-06-24 | Devanshu |  | 2026-06-24 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Painting has been put on hold; 4 parts remaining; Other projects have been picked up for joining and painting | Needs to be done by Anurag | Rapid Proto; | 2026-06-27 | Anurag |  | 2026-06-24 | Plastic
AutoDyanamics | C5283 | Machining | 8 (split parts) | 2026-06-17 |  | 0 | 8 | Some parts (7) have come today and some (16) will come tomorrow; Pandhurinath will be in the office tomorrow; | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-24 | Metal
AutoDyanamics | C5285 | Machining | 15 (split parts) | 2026-06-17 |  | 0 | 15 | Some parts (7) have come today and some (16) will come tomorrow; Pandhurinath will be in the office tomorrow; | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-24 | Metal
Enertics | C5230 | [6 empty] | 320 pending will be sent after the payment is released; Work is completed |  | PlastoFur | 2026-06-24 | Anurag |  | 2026-06-24 | Metal
Labat Asia | C5195 | VC ABS Grey Painting | 150 | 2026-05-05 |  | 93 | 57 | It is not urgent as per the customer so kept on hold; Inserting is pending which will be done by Arjun after other projects are completed | Needs to be done by Anurag | Excel | Delayed as per conversation with the customer | Shubham/Anurag |  | 2026-06-24 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Monday; Design has been sent; Payment is pending; Bharat will have to be in the office; Shubham needs to debrief Bharat; Zoom meeting has to be done ; Meeting still pending; scheduled after lunch |  | CICU; |  | Shubham |  | 2026-06-24 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | 9 have reached; 27 will be sent to EngLabs on Friday ; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-24 | Plastic
Sonalika | C5262 | MJF Black Paint | 4 | 2026-06-06 |  | 0 | 4 | Sent on Saturday; Delivered; Feedback pending | Anurag | Excel; | 2026-06-26 | Shubham |  | 2026-06-24 | Plastic
HC Robotics | C5273 | MJF | 64 | 2026-06-12 |  | 0 | 64 | Update pending; parts should come today | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-24 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Will be sent to us by vendor today; QC will be done by Anurag and needs to be sent on Wed | Shubham | SK Techno | 2026-06-24 | Shubham |  | 2026-06-24 | Metal
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Delayed by Courier; Will come today; Painting to be ready by Fri; No PO | Anurag | idemi | 2026-06-27 | Shubham |  | 2026-06-24 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture; Will be ready by 25th June and sent to Englabs by Saturday; No PO; Update from Vendor needs to be taken | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-24 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will Manufacture; Will be ready by 25th June and sent to Englabs by Saturday; No PO; Update from Vendor needs to be taken | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-24 | Plastic
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture; Expected from vendor by Friday | Anurag | Adroitec | Expected 27-06-2026 | Shubham |  | 2026-06-24 | Plastic
HC Robotics | C5295 | MJF/PA12 NYLON/Aircraft grey or Black outside only | 4 | 2026-06-22 | ASAP | 0 | 4 | PO from the vendor has come today; Should come to EngLabs by Friday; Painting should happen on Saturday | Devanshu | Adroitec | 2026-06-29 | Devanshu |  | 2026-06-24 | Plastic
Bajaj | C5264 | MJF+SLA; Glass Filled, Transparent | 73 | 2026-06-23 | ASAP | 0 | 73 | Vendor has not been flinalised yet; quote evaluation is happening | Devanshu | TBD | 2026-06-29 | Devanshu |  | 2026-06-24 | Plastic
Bajaj | C5255 | VC Rubber | 20 | 23-06-2026 |  | 0 | 20 | Will start manufacturing | Devanshu | Excel | 2026-07-04 | Devanshu |  | 2026-06-24 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Completed; QC done visually; Packaging checked by Shubham; Thursday feedback | Done | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-24 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Dispatched to customer; Feedback on Thursday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-24 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Dispatched to customer; Feedback on Thursday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-24 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken next week; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-24 | Plastic
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | SK Techno |  | Shubham |  | 2026-06-24 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO is needed; Payment done | Shubham | SK Techno |  | Shubham |  | 2026-06-24 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Delivered; QC was done by Rohit; Feedback will be taken by Rohit | Devanshu | Adroitec | 22-06-2026 | Devanshu |  | 2026-06-24 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today; QC was done by Rohit; Feedback will be taken by Rohit | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-24 | Plastic
Labat Asia | C5233 | ABS | 55+55 |  |  | 0 | 110 | Parts are there; Painting on hold | Anurag |  |  |  |  | 2026-06-24
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Joining has started; Need more resources to complete this | Anurag | Rapid Proto; | Expected 27-06-2026 | Shubham |  | 2026-06-25 | Plastic
Aebocode | C5296 | MJF | 14 | 2026-06-19 |  | 0 | 14 | Delivered yesterday; Feedback taken; Anurag has to send documented feedback | Anurag | Adroitec | 2026-06-24 | Devanshu |  | 2026-06-25 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | Painting has been put on hold; 4 parts remaining; Other projects have been picked up for joining and painting | Needs to be done by Anurag | Rapid Proto; | 2026-06-27 | Anurag |  | 2026-06-25 | Plastic
AutoDyanamics | C5283 | Machining | 8 (split parts) | 2026-06-17 |  | 0 | 8 | Some parts (7) have been completed and some (16) will come tomorrow; Pandhurinathis in the office | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-25 | Metal
AutoDyanamics | C5285 | Machining | 15 (split parts) | 2026-06-17 |  | 0 | 15 | Some parts (7) have been completed and some (16) will come tomorrow; Pandhurinathis in the office | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-25 | Metal
Enertics | C5230 | [6 empty] | 320 pending will be sent after the payment is released; Work is completed |  | PlastoFur | 2026-06-24 | Anurag |  | 2026-06-25 | Metal
Labat Asia | C5195 | VC ABS Grey Painting | 150 | 2026-05-05 |  | 93 | 57 | It is not urgent as per the customer so kept on hold; Inserting is pending which will be done by Arjun after other projects are completed | Needs to be done by Anurag | Excel | Delayed as per conversation with the customer | Shubham/Anurag |  | 2026-06-25 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Meeting done yesterday; Designer will give the updated file today |  | CICU; |  | Shubham |  | 2026-06-25 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | 9 have reached; 27 will be sent to EngLabs on Friday ; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-25 | Plastic
Sonalika | C5262 | MJF Black Paint | 4 | 2026-06-06 |  | 0 | 4 | Sent on Saturday; Delivered; Feedback pending | Anurag | Excel; | 2026-06-26 | Shubham |  | 2026-06-25 | Plastic | [8 empty] | Parts were good as per the fitment; Inserts were okay; Timely delivery should be there
HC Robotics | C5273 | MJF | 64 | 2026-06-12 |  | 0 | 64 | 2 parts are pending; should get delivered today | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-25 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | On the way; should get delivered today | Shubham | SK Techno | 2026-06-24 | Shubham |  | 2026-06-25 | Metal
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Primer being done right now; Painting will be done after that; PO Awaited | Anurag | idemi | 2026-06-27 | Shubham |  | 2026-06-25 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will Manufacture; Will be ready by 25th June and sent to Englabs by Saturday; No PO; Update from Vendor needs to be taken | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-25 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will Manufacture; Will be ready by 25th June and sent to Englabs by Saturday; No PO; Update from Vendor needs to be taken | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-25 | Plastic
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture; Expected from vendor by Saturday | Anurag | Adroitec | Expected 27-06-2026 | Shubham |  | 2026-06-25 | Plastic
HC Robotics | C5295 | MJF/PA12 NYLON/Aircraft grey or Black outside only | 4 | 2026-06-22 | ASAP | 0 | 4 | PO from the vendor has come today; Should come to EngLabs by Friday; Painting should happen on Saturday | Devanshu | Adroitec | 2026-06-29 | Devanshu |  | 2026-06-25 | Plastic
Bajaj | C5264 | MJF+SLA; Glass Filled, Transparent | 73 | 2026-06-23 | ASAP | 0 | 73 | Vendor will send on Monday; Inserts and painting has to be done | Devanshu | Objectify | 2026-06-29 | Devanshu |  | 2026-06-25 | Plastic
Bajaj | C5255 | VC Rubber | 20 | 23-06-2026 |  | 0 | 20 | Will start manufacturing | Devanshu | Excel | 2026-07-04 | Devanshu |  | 2026-06-25 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Completed; QC done visually; Packaging checked by Shubham; Thursday feedback | Done | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-25 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Dispatched to customer; Feedback on Thursday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-25 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Dispatched to customer; Feedback on Thursday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-25 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken next week; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-25 | Plastic
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | SK Techno |  | Shubham |  | 2026-06-25 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO is needed; Payment done | Shubham | SK Techno |  | Shubham |  | 2026-06-25 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Delivered; QC was done by Rohit; Feedback will be taken by Rohit | Devanshu | Adroitec | 22-06-2026 | Devanshu |  | 2026-06-25 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today; QC was done by Rohit; Feedback will be taken by Rohit | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-25 | Plastic
Labat Asia | C5233 | ABS | 55+55 | 2025-11-01 |  | 0 | 110 | Parts are there; Painting on hold. Payment has not been done | Anurag | China |  | Anurag |  | 2026-06-25 | Plastic
AV Machining | C5023 | MJF | 135 | 2026-06-04 |  | 0 | 135 | Joining still going on | Anurag | Rapid Proto; | 2026-06-29 | Shubham |  | 2026-06-26 | Plastic
Aebocode | C5296 | MJF | 14 | 2026-06-19 |  | 0 | 14 | Delivered yesterday; Feedback taken; Anurag has to send documented feedback | Anurag | Adroitec | 2026-06-24 | Devanshu |  | 2026-06-26 | Plastic
Sonalika | C5251 | MJF Black Paint | 32 | 2026-06-05 |  | 0 | 32 | 11 are ready to be given; Gaurav will visit around 11 am and take these parts; QC has to be done; Rest of the parts can be taken up by Monday | Needs to be done by Anurag | Rapid Proto; | 2026-06-27 | Anurag |  | 2026-06-26 | Plastic
AutoDyanamics | C5283 | Machining | 8 (split parts) | 2026-06-17 |  | 0 | 8 | 11 will be taken by Pandhurinathis; Others will be sent on Monday | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-26 | Metal
AutoDyanamics | C5285 | Machining | 15 (split parts) | 2026-06-17 |  | 0 | 15 | 11 will be taken by Pandhurinathis; Others will be sent on Monday | Anurag | Talekar | Expected 26-06-2026 | Shubham |  | 2026-06-26 | Metal
Enertics | C5230 | [6 empty] | 220 are being sent today |  | PlastoFur | 2026-06-24 | Anurag |  | 2026-06-26 | Metal
Labat Asia | C5195 | VC ABS Grey Painting | 150 | 2026-05-05 |  | 93 | 57 | It is not urgent as per the customer so kept on hold; Inserting is pending which will be done by Arjun after other projects are completed | Needs to be done by Anurag | Excel | Delayed as per conversation with the customer | Shubham/Anurag |  | 2026-06-26 | Plastic
SARK | C5239 | Scanning Modelling | 7 | 2026-05-30 |  | 0 | 7 | Design final; Sampling will be done by WorkEd |  | CICU; |  | Shubham |  | 2026-06-26 | Plastic
Sonalika | C5254 | MJF Black Paint | 36 | 2026-06-06 |  | 0 | 36 | 9 have reached; 27 will be sent to EngLabs on Friday ; PO Awaited |  | Half frm PlastiPack; Half from Rapid Proto | 2026-06-23 | Shubham |  | 2026-06-26 | Plastic
Sonalika | C5262 | MJF Black Paint | 4 | 2026-06-06 |  | 0 | 4 | Sent on Saturday; Delivered; Feedback pending | Anurag | Excel; | 2026-06-26 | Shubham |  | 2026-06-26 | Plastic
HC Robotics | C5273 | MJF | 64 | 2026-06-12 |  | 0 | 64 | 2 parts are pending; should get delivered today | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-26 | Plastic
Bajaj | C5248 | MS Machining | 10 | 2026-06-08 |  | 0 | 10 | Processing has to be done; Arjun has to do today | Shubham | SK Techno | 2026-06-24 | Shubham |  | 2026-06-26 | Metal
Sonalika | C5286 | MJF | 10 | 2026-06-12 |  | 0 | 10 | Primer being done right now; Painting will be done after that; PO Awaited | Anurag | idemi | 2026-06-27 | Shubham |  | 2026-06-26 | Plastic
Sonalika | C5280 | VC | 15 | 2026-06-12 |  | 0 | 15 | Will come on Monday from the vendor; Visual QC to be done and sent on Tuesday; PO awaited | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-26 | Plastic
Sonalika | C5267 | VC | 14 | 2026-06-12 |  | 0 | 14 | Will come on Monday from the vendor; Visual QC to be done and sent on Tuesday; PO awaited | Anurag | excel Rapid Tech | 2026-06-29 | Devyanshu |  | 2026-06-26 | Plastic
Aebocode | C5292 | MJF | 25 | 2026-06-18 |  | 0 | 25 | Will Manufacture; Expected from vendor by Saturday | Anurag | Adroitec | Expected 27-06-2026 | Shubham |  | 2026-06-26 | Plastic
HC Robotics | C5295 | MJF/PA12 NYLON/Aircraft grey or Black outside only | 4 | 2026-06-22 | ASAP | 0 | 4 | PO from the vendor has come today; Should come to EngLabs by Friday; Painting should happen on Saturday | Devanshu | Adroitec | 2026-06-29 | Devanshu |  | 2026-06-26 | Plastic
Bajaj | C5264 | MJF+SLA; Glass Filled, Transparent | 73 | 2026-06-23 | ASAP | 0 | 73 | Vendor will send on Monday; Inserts and painting has to be done | Devanshu | Objectify | 2026-06-29 | Devanshu |  | 2026-06-26 | Plastic
Bajaj | C5255 | VC Rubber | 20 | 23-06-2026 |  | 0 | 20 | Started; Delivery expected next week | Devanshu | Excel | 2026-07-04 | Devanshu |  | 2026-06-26 | Plastic
AV Machining | C5023 | VC PP | 90 | 2026-05-23 |  | 0 | 90 | Completed; QC done visually; Packaging checked by Shubham; Thursday feedback | Done | excel Rapid Tech | 2026-06-20 | Shubham |  | 2026-06-26 | Plastic
Sonalika | C5232 | MJF Black Paint | 5 | 2026-06-12 |  | 0 | 5 | Dispatched to customer; Feedback on Thursday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-26 | Plastic
Sonalika | C5231 | MJF Black Paint | 2 | 2026-06-12 |  | 0 | 2 | Dispatched to customer; Feedback on Thursday | Anurag | excel Rapid Tech | 2026-06-26 | Devyanshu |  | 2026-06-26 | Plastic
Parikalpana | C5275 | MJF | 6 | 2026-06-11 |  | 0 | 6 | Sent on 16th; Feedback has to be taken next week; Status closed; Shubham has already asked for feedback | Visual done by Shubham | Adroitec |  | Shubham |  | 2026-06-26 | Plastic
Bajaj | C5237 | Machining !! SIA ABS | 17 | 2026-06-09 |  | 0 | 17 | Delivered on 17th; Feedback will be sent by customer next week; Formal email request to be sent for testimonial | Visual done by Shubham | SK Techno |  | Shubham |  | 2026-06-26 | Metal
Menthosa | C5279 | Machining | 4 | 2026-06-12 |  | 0 | 4 | Delivered on 17th; Machine so no painting; Feedback will have to be taken; No PO is needed; Payment done | Shubham | SK Techno |  | Shubham |  | 2026-06-26 | Plastic
BCH | C5152 | SLS Raw | 8 | 2026-06-15 |  | 0 | 8 | Delivered; QC was done by Rohit; Feedback will be taken by Rohit | Devanshu | Adroitec | 22-06-2026 | Devanshu |  | 2026-06-26 | Plastic
Orient | C5088 | SLS ABS | 11 | 2026-06-10 |  | 0 | 11 | Rohit has delivered today; QC was done by Rohit; Feedback will be taken by Rohit | Rohit | CADQUA | 2026-06-18 | Devanshu |  | 2026-06-26 | Plastic
Labat Asia | C5233 | ABS | 55+55 | 2025-11-01 |  | 0 | 110 | Parts are there; Painting on hold. Payment has not been done | Anurag | China |  | Anurag |  | 2026-06-26 | Plastic

## Color Code
Colour | Operations Status
Work has to happen today in EngLabs
Follow up with vendor to ensure timely delivery
Delivered but feedback not taken
Delivered and feedback taken
Hold at client end

## Vendor Operations
Task | Project | Customer | Vendor | Parts | Update | Date
Total have to come by Friday | C5267 | Sonalika | Excel | 14 | 4 will come today; Only mould is ready till now; This will get delayed | 2026-06-22
Total have to come by Wednesday | C5273 | HC Robotics | Excel | 64 | No update on how many done; But will send today | 2026-06-22
All parts should come today | C5296 | Aebocode | Adroitec | 14 | Only 4 ready | 2026-06-22
All parts should come by Friday | C5280 | Sonalika | Excel | 15 |  | 2026-06-22
All parts should come today | C5286 | Sonilika | Idemi | 10 | Will send by today via DTDC | 2026-06-22
All parts should come today | C5023 | AV Machining | Rapid Proto | 135 | Have reached the airport; Gurpreet will go again in the evening | 2026-06-22
All parts should come by tomorrow | C5248 | Bajaj | SK Techno | 10 | Anurag has not called yet | 2026-06-22
All parts should be dispatched tomorrow | C5254 | Sonalika | PlastiPak and Rapid Proto | 36 | Should get deliverd by 25-06-2026; One set is ready | 2026-06-22
Talekar has to send today | C5283 and C5285 | Auto Dynamics | Talekar | 6 and 9 | It will be sent tomorrow | 2026-06-22
| C5262 | Sonalisa | Excel | 14 | Follow up pending | 2026-06-23
Total have to come by Friday | C5267 | Sonalika | Excel | 14 | 4 will come today; Only mould is ready till now; This will get delayed | 2026-06-23
Total have to come by Wednesday | C5273 | HC Robotics | Excel | 64 | Around 10-12; Should come today | 2026-06-23
All parts should come today | C5296 | Aebocode | Adroitec | 14 | Only 4 ready; Should come by Friday | 2026-06-23
All parts should come by Friday | C5280 | Sonalika | Excel | 15 | Delayed; Should come by Saturday | 2026-06-23
All parts should come today | C5286 | Sonilika | Idemi | 10 | Will come tomorrow; Delayed | 2026-06-23
All parts should come today | C5023 | AV Machining | Rapid Proto | 135 | Have reached the airport; Gurpreet will go again in the evening | 2026-06-23
All parts should come by tomorrow | C5248 | Bajaj | SK Techno | 10 | Anurag has not called yet | 2026-06-23
All parts should be dispatched tomorrow | C5254 | Sonalika | PlastiPak and Rapid Proto | 36 | Should get deliverd by 25-06-2026; One set is ready | 2026-06-23
Talekar has to send today | C5283 and C5285 | Auto Dynamics | Talekar | 6 and 9 | It will be sent today; Joining and painting will have to be done | 2026-06-23

## Others
Date | Notes
25 parts done; 50 more parts pending for sanding; Putty done for all the parts for AV Machining; 10 parts being picked for LABAT
Task | Owner | Timeline | Notes | Date of Standup
Update Enq Register | Aruti | Today | From 18th to 20th and 27th to 1st | 2026-06-02
Update Address in the Vendor List | Aruti | Today | Add the City and Full Address | 2026-06-02
Identify Pune Based Vendors and request site visit and meeting for this week | Shubham | Today
Finalise meeting with potential vendor - Pioneer | Larissa | Today
Get the feedback from Vibracoustic | Shubham | Next Week
Henkel Bajaj EndurAir Orient Quotation Follow Up | Shubham | Next Week
Email from Brittania; They are okay with the cost; They need documents from EngLabs; Scanning guys need to be sent to Gwalior; Email was sent to Bharat; Check with Bharat if he is working on it else work on the letter head; | Shubham | This Week
Follow up with marketing team of Kapyah | Aruti | Today
Presentation should be ready
Collateral Folder
Check with Ratnesh for payment; Atomberg AV Henkel payment done |  | Done
Visit to Elin and Mobility Techno Plastic Group SEB; Swaraj
Jal Joy
Aruti to work with Shubham to send 3d Data of Daikin to Pioneer and check if they will do it; Quote
Follow up with PRG Tech; SG Engineering; SML; Indrones, Passim
Emectec
One Drive Issue - data gets auto delete; sync not happening from Shubham's desktop
Check if paint is done for HC Robotics |  | Done
Finalise meetingwith Baddi clients for Friday | Shreeya | Done | Meeting fixed with Elin, Group SEB and Yash Appliances
Sunday could be a working day; Salil will confirm on Saturday morning; Anurag will inform everyone; Operations and post processing team
Shreeya needs to join the call to give payments status
Sonalika parts 5232 and 5231 should be completed on Sunday
Salil to review testimonials
Make the QC Sheet and follow that for visual QC and dispatch to the clients
Bajaj payment will have to be added to the payments sheet
Menthosa payment will have to be added to the payments sheet
Devyanshu to shadow Anurag for QC
PI will have to be sent to AutoDynamics
Payment for AutoDynamics will have to be updated in the payments sheet |  | Done
Shubham will talk to Excel for QC Sheets
Reschedule SARK meeting to Tuesday |  |  |  | 2026-06-20
Feedback from AV Machining has to be taken on Tuesday |  |  |  | 2026-06-20
Devanshu needs to call Excel and follow up for HC Robitics work on Monday |  |  |  | 2026-06-20
BCH and Orient feedback to be taken by Rohit |  |  |  | 2026-06-20
Shubham/Devanshu; C5254; Dispatch from Plastipack and RapidProto has to happen tomorrow |  |  |  | 2026-06-22
SARK check with Shubham if the meeting has been rescheduled for Tuesday |  |  |  | 2026-06-22
Reminder to SK Techno for C5248 - Anurag; Dispatch from vendor on Tuesday |  |  |  | 2026-06-22
C5280 and C5267 - check with Excel; Expected by Friday - Devanshu |  |  |  | 2026-06-22
Shubham/Devanshu needs to confirm if C5286 will be delivered today by iDemi |  |  |  | 2026-06-22
C5283 aand C5285 - Gurpreet has to bring from the airport; Autodynamics; Painting has to start after that |  |  |  | 2026-06-22
C5023 dispatch was supposed to be done on Sunday by Rapid Proto; Check with Shubham |  |  |  | 2026-06-22
C5296 Aebocode - check with Excell; has to be delivered today; confirm with Shubham - excel or adroitec |  |  |  | 2026-06-22
Print Brochures |  |  |  | 2026-06-22
Shubham needs to finalise the vendor for C5295 and give the go ahead to send |  |  |  | 2026-06-22
Diaries
Photo Booth
Content Creation - EngLabs Instagram Page
Resource going to the airport has to reach in time
Headsup to Ajay Shinde - Shubham and Rohit
Anurag - QC has to be done for Sonalika parts
Plastipak coordination for 27 parts
Excel for C5273; should be delivered today
Arjun C248
Gloves need to be ordered
Shubham to give notes on pending payment of vendor
Adroitec follow up for Aebocode C25292
C5295 follow up with Adroitec 4 parts

## Sales
Link to Enquiries Register
Task | Customer | Date | Owner | Sales/Marketing | Status
Connected with Pioneer to discuss the Daikin Sheet Metal project with him and also ask about projects that they can provide us; NdA has been sent to them | Pioneer | 2026-06-11 |  | Sales
More calls were done to get meetings in Baddi; Only 4 have been setup for now |  | 2026-06-11 |  | Marketing
Send quotation and feasibility analysis to JCBL; Call done by Shubham with the vendor on Saturday; Details will be shared with the customer on Tuesday/Wed depending on the response from the vendor | JCBL | 2026-06-22 | Shubham | Sales
Send thank you note to the JCBL for the meeting; share the NDA ; Follow up for the visit as well | JCBL | 2026-06-22 | Shreeya | Marketing
Send thank you note to Spray for the meeting; Follow up with Surjit for the RFQ; Follow up with Abhinav for the RFQ of his friends' project by next week | Spray | 2026-06-22 | Shreeya | Sales
Follow up with Shaminder for details related to cap project shared by him; Arrange a call between Shaminder and Shubham | Spray | 2026-06-22 | Shreeya | Sales
Follow up with Pioneer for next steps on Tuesday | Pioneer | 2026-06-22 | Shubham | Sales
Send thank you note to Aveer for the meeting | Aveer | 2026-06-22 | Shreeya | Marketing
Send revised quotation to Nikhil Jagtap if price change is possible else inform him accordingly; Shubham will check if price can be reduced; Ratnesh will make changes to the quote accordingly | Bajaj | 2026-06-22 | Shubham/Ratnesh | Sales
Send quotation to Pandharinath from AutoDynamics; Ratnesh will prepare the quotation based on the timeline/price confirmation from Shubham | AutoDynamics | 2026-06-22 | Shubham/Ratnesh | Sales
Send quotation to Vishal from Bajaj; Ratnesh will prepare the quotation based on the timeline/price confirmation from Shubham | Bajaj | 2026-06-22 | Shubham/Ratnesh | Sales
Send quotation to Pawan from VNG Medical | VNG Medical | 2026-06-22 | Shubham/Ratnesh | Sales
Call prospects as per the marketing list and share the status by Friday | Prospects | 2026-06-22 | Larissa/Shreeya/Rohit | Business Development
Send quotation and feasibility analysis to JCBL; Call done by Shubham with the vendor on Saturday; Details will be shared with the customer on Tuesday/Wed depending on the response from the vendor | JCBL | 2026-06-23 | Shubham | Sales | Client did not pick up the phone
Work on the NDA ; Follow up for the visit as well | JCBL | 2026-06-23 | Shreeya | Marketing | Pending
Follow up with Surjit for the RFQ; Follow up with Abhinav for the RFQ of his friends' project by next week | Spray | 2026-06-23 | Shreeya | Sales | Pending
Follow up with Shaminder for details related to cap project shared by him; Arrange a call between Shaminder and Shubham | Spray | 2026-06-23 | Shreeya | Sales | Client will send the sample
Follow up with Pioneer for next steps on Tuesday | Pioneer | 2026-06-23 | Shubham | Sales | Pending
Send thank you note to Aveer for the meeting on WhatsApp | Aveer | 2026-06-23 | Shreeya | Marketing | Pending
Send revised quotation to Nikhil Jagtap | Bajaj | 2026-06-23 | Shubham/Ratnesh | Sales | Order Lost as other projects have been given to EngLabs
Send quotation to Vishal from Bajaj; | Bajaj | 2026-06-23 | Shubham/Ratnesh | Sales | Sent
Send quotation to Pawan from VNG Medical | VNG Medical | 2026-06-23 | Shubham/Ratnesh | Sales | Sent
Call prospects as per the marketing list and share the status by Friday | Prospects | 2026-06-23 | Larissa/Shreeya/Rohit | Business Development | On-Going
Send quotation to Anuj Gupta from VibraCoustic | VibraCoustic | 2026-06-23 | Shubham | Sales | Sent
Send quotation to Avinash (2 parts, 10 each, MS) | OrientElectric | 2026-06-24 | Shubham | Sales | Sent
Send quotation to Pandharinath from AutoDynamics; 1 Qty VMC Machining; PA66 GF30% | AutoDynamics | 2026-06-24 | Shubham | Sales | On-Going
Send quotation | Havells | 2026-06-24 | Shubham | Sales | On-Going
Send quotation | Yash Appliances | 2026-06-24 | Shubham | Sales | Sent
Send quotation | Sonalika | 2026-06-24 | Shubham | Sales | Sent
Send quotation | Bajaj | 2026-06-25 | Shubham | Sales
Send quotation | Microtek | 2026-06-26 | Shubham | Sales

## Marketing
Task | Owner | Category | Timeline | Status
Lead Generation
Lead Generation
Branding
Events
Carbon Fibre Case Study |  | Content for Collateral
Content for Social Media
Website
SEO
Posts on Social Media
Reporting
Baddi Visits; |  | Client Visits |  | Check with Shreeya
Prepare the marketing kit for Pune

## Payments
S No | Accounts Update Date | PARTICULARS | Due Amount(as of today) | AMOUNT | AS ON | Contact | Phone | HANDLE BY | Follow Up to be Done | REMARKS on Payment Received | DUE ON | last correspondence on | Payment Terms
2026-06-18
1 | June 18-2026 | AEBOCODE TECHNOLOGIES | 256323 | 262955 | 18-06-2026 |  |  | BHARAT SIR | Bharat needs to be ask for the payment and order also | 3,00,000 on May 22; Message dropped; no response yet
2 | June 18-2026 | AVEER INDUSTRIES |  | Nil | 18-06-2026 | Mandeep | 90411 89436; 9672610034 Saurabh for payment | SHUBHAM SIR | Payment will be done by end of this week / saurabh did not reply | 3717/- rec on 16 june 2026 | 2026-06-04
3 | June 18-2026 | BAJAJ ELECTRICALS LIMITED |  | 76945 | 18-06-2026 |  |  | RATNESH |  | DUE ON 16 JULY 2026 76945/-
4 | June 18-2026 | ENDURAIR SYSTEMS PVT LTD | 76834 | 97634 | 18-06-2026 |  |  | SHUBHAM SIR | Shreeya talked to Ankur payment will be done by today | 1,15,445 received on June 6, 2026 | 65,052 due after May 31; 27824 due on 3 July
5 | June 18-2026 | GROUP SEB |  | NIl | 18-06-2026
6 | June 18-2026 | HAVELLS INDIA LIMITED |  | NIl | 18-06-2026
7 | June 18-2026 | HELLA INDIA | 27122 | 65077 | 18-06-2026 |  |  | BHARAT SIR | Wait till June 26; Shubham will check after that |  | 26 June 2026; As of due 27122
8 | June 18-2026 | ITL SONALIKA | 179156 | 195156 | 18-06-2026 |  |  | Shubham sir | Payment to come this week pending invoices shared with Ra | 75080/- rec on 17 june
9 | June 18-2026 | MY DESIGN MINDS | He is in debt | 103642 | 18-06-2026 |  |  | Shubham sir | Wait till June 30 | 50000/- ON 16 MAY | all due
10 | June 18-2026 | ORIENT ELECTRIC LIMITED |  | 63738 | 18-06-2026 |  |  | Rohit sir | Rohit and Shubham | 19,387 due on June 12; 30,042 due on June 21; 25,879 on July 4 | 7816/- 09 march 2026
11 | June 18-2026 | ELIN APPLIANCES |  | NIl | 18-06-2026 |  |  |  | Aruti
12 | June 18-2026 | mobility solution |  | 65161 | 18-06-2026 | Mr. Manu | +91 87250 68321 | shubham sir | Bharat needs to visit | Payment was pending so reports were kept on hold; | all due since April 16
13 | June 18-2026 | Jal bath |  | Nil | 18-06-2026
14 | June 18-2026 | kyocera avx |  | Nil | 18-06-2026 | Mr. Nishant | 930466 8342 | SHUBHAM SIR | Aruti | 21421/- rec on 17 june 2026 | 2026-06-07
15 | June 18-2026 | microtek |  | 5612 | 18-06-2026 |  |  | SHUBHAM SIR | Aruti | 25626/- rec on 17 june 2026 | all due by 11 may
16 | June 18-2026 | techno plastic |  | Nil | 18-06-2026
17 | June 18-2026 | NIPA | 16307 | 41782 | 18-06-2026 |  |  | RATNESH | No need to follow up | 4307 received on May 31; 16307 due on June 3; 11351 due on June 11; 22078 due on Jun 18; 3398 due on June 24 | 4307/- 21 may
18 | June 18-2026 | Modern manufeactures |  | Nil | 18-06-2026 |  |  | -----------
19 | June 18-2026 | AV MACHINING SOLUTION |  | 419275 | 18-06-2026 |  |  | ROHIT SIR shubham | Aruti; follow up on Tuesday for 2-3 Lakhs | 1,00,000 received on June 6 |  |  | To be finalised by Bharat
20 | June 18-2026 | DAIKIN AIRCONDITIONING |  | Nil | 18-06-2026
21 | June 18-2026 | HENKEL ANAND |  | 280486 | 18-06-2026 |  |  | SHUBHAM SIR | No need to follow up | 147421 received on June 4; Payment will be done this week and PO will be raised
22 | June 18-2026 | LABAT ASIA |  | 171535 | 18-06-2026 | Mr. deepak | 70870 32512 | Ratnesh | Check on Wed; Ledger on Monday | 22374/- 15 MAY & 12743/- 13 MAY; Payment will be done this week | 89k all due
23 | June 18-2026 | MARELLI (INDIA) |  | Nil | 18-06-2026 |  |  | ---------- |  | 45136/- ON 15 MAY; 9211 on May 25 | 45136/- by 11 may |  | To be finalised by Bharat
24 | June 18-2026 | PRG TECH |  | Nil | 18-06-2026
25 | June 18-2026 | SG ENGINEERING |  | 413 | 18-06-2026 |  |  | ---------- | No need to follow up
26 | June 18-2026 | SIMSUN INNOTECH |  | 19790 | 18-06-2026 |  |  | SHUBHAM SIR |  |  | all due
27 | June 18-2026 | SML MAHINDRA |  | Nil | 18-06-2026
28 | June 18-2026 | YASH AIRTECH | 52534 | 52534 | 18-06-2026 | Mr.sanjeev | 82196 06827 | RATNESH | Aruti | 16960 on May 26; payment will be done by end of this week | all due
29 | June 18-2026 | GOEL ENTERPRISES |  | 42480 | 18-06-2026 | Mr. Avdeesh +91 988050826 |  | ---------- | Aruti | Invoice was sent on May 29; Email sent again as per the request of the customer | no due date
30 | June 18-2026 | INDRONES |  | Nil | 18-06-2026 |  |  | ----------
31 | June 18-2026 | PASSIM |  | Nil | 18-06-2026 |  |  | ----------
32 | June 18-2026 | BAAZ BIKES |  | Nil | 18-06-2026 |  |  | ----------
33 | June 18-2026 | UNO MINDA (VTT ENGCON) |  | 303732 | 18-06-2026 | Mr. Manoj | 88021 62267 | ---------- | Aruti; wait till June 25 ( VTT GROUP ) | 2025-06-01
34 | June 18-2026 | EMETEC SOLUTION |  | Nil | 18-06-2026 |  |  | shubham sir
35 | June 18-2026 | AMISON ENGENEERING |  | Nil | 18-06-2026
36 | June 18-2026 | ATOMBERG |  | 23010 | 18-06-2026 | Mr. Vivek patil | 93092 55409 |  | Wait to follow up; Aruti | 23600 received on June 3, 2026; | 2026-06-25
37 | June 18-2026 | sark industries |  | Nil | 18-06-2026 |  |  |  |  | 1770 payment came on May 28
38 | June 18-2026 | RAPID PROTO |  | Nil | 18-06-2026 |  |  | SHUBHAM SIR |  |  | 2026-06-13
39 | June 18-2026 | scope medical | 6101 | 6101 | 18-06-2026 |  |  |  | Shubham needs to follow up
40 | June 18-2026 | Enertics | 47253 | 47253 | 18-06-2026 |  |  | Bharat | Ask Bharat | Invoice was sent on June 5;
41 | June 18-2026 | HC Robotics | 1770 | 135495 | 18-06-2026 |  |  | SHUBHAM SIR | Ask Shubham after 22 June | 335082 on 20 June; 24553 on 21 June; 74090 on 22 June
42 | June 18-2026 | PPI Proto Plasts India | 4484 | 4484 | 18-06-2026 |  |  | SHUBHAM SIR | Shubham will follow up | 4484 on March 21 Payment will be done this week
43 | June 18-2026 | menthosa |  | Nil | 18-06-2026 |  |  |  |  | 25370/- rec on june 2026
44 | June 18-2026 | PARAM APPLIANCES | 4234 | 4234 | 18-06-2026
| June 18-2026 | TOTAL | 667884 | 2484290
2026-06-16
1 | June 16-2026 | AEBOCODE TECHNOLOGIES |  | 256323 | 2026-06-06 |  |  | BHARAT SIR | Bharat needs to be ask for the payment and order also | 3,00,000 on May 22; Message dropped; no response yet
2 | June 16-2026 | AVEER INDUSTRIES |  | 3717 | 2026-06-06 | Mandeep | 90411 89436; 9672610034 Saurabh for payment | SHUBHAM SIR | Payment will be done by end of this week / saurabh did not reply |  | 2026-06-04
3 | June 16-2026 | BAJAJ ELECTRICALS LIMITED |  | Nil | 2026-06-06 |  |  | RATNESH |  | Received on June 1; 6071
4 | June 16-2026 | ENDURAIR SYSTEMS PVT LTD | 76834 | 97634 | 2026-06-06 |  |  | SHUBHAM SIR | Shreeya talked to Ankur payment will be done by today | 1,15,445 received on June 6, 2026 | 65,052 due after May 31; 27824 due on 3 July
5 | June 16-2026 | GROUP SEB |  | NIl | 2026-06-06
6 | June 16-2026 | HAVELLS INDIA LIMITED |  | NIl | 2026-06-06
7 | June 16-2026 | HELLA INDIA | 27122 | 65077 | 2026-06-06 |  |  | BHARAT SIR | Wait till June 26; Shubham will check after that |  | 26 June 2026; As of due 27122
8 | June 16-2026 | ITL SONALIKA | 254236 | 270236 | 2026-06-06 |  |  | Shubham sir | Payment to come this week pending invoices shared with Ra | 118150 is already due on June 3; 127522 due on June 10; 8467 due on June 24
9 | June 16-2026 | MY DESIGN MINDS |  | 103642 | 2026-06-06 |  |  | Shubham sir | Wait till June 30; He is in debt | 50000/- ON 16 MAY | all due
10 | June 16-2026 | ORIENT ELECTRIC LIMITED |  | 63738 | 2026-06-06 |  |  | Rohit sir | Rohit and Shubham | 19,387 due on June 12; 30,042 due on June 21; 25,879 on July 4 | 7816/- 09 march 2026
11 | June 16-2026 | ELIN APPLIANCES |  | NIl | 2026-06-06 |  |  |  | Aruti
12 | June 16-2026 | mobility solution |  | 65161 | 2026-06-06 | Mr. Manu | +91 87250 68321 | shubham sir | Bharat needs to visit | Payment was pending so reports were kept on hold; | all due since April 16
13 | June 16-2026 | Jal bath |  | Nil | 2026-06-06
14 | June 16-2026 | kyocera avx |  | 21441 | 2026-06-06 | Mr. Nishant | 930466 8342 | SHUBHAM SIR | Aruti | Payment will be done this week | 2026-06-07
15 | June 16-2026 | microtek | 23210 | 31239 | 2026-06-06 |  |  | SHUBHAM SIR | Aruti | Invoices sent on Whatsapp; Payment will be done in 2-3 days | all due by 11 may
16 | June 16-2026 | techno plastic |  | Nil | 2026-06-06
17 | June 16-2026 | NIPA | 16307 | 41782 | 2026-06-06 |  |  | RATNESH | No need to follow up | 4307 received on May 31; 16307 due on June 3; 11351 due on June 11; 22078 due on Jun 18; 3398 due on June 24 | 4307/- 21 may
18 | June 16-2026 | Modern manufeactures |  | Nil | 2026-06-06 |  |  | -----------
19 | June 16-2026 | AV MACHINING SOLUTION |  | 419275 | 2026-06-06 |  |  | ROHIT SIR shubham | Aruti; follow up on Tuesday for 2-3 Lakhs | 1,00,000 received on June 6 |  |  | To be finalised by Bharat
20 | June 16-2026 | DAIKIN AIRCONDITIONING |  | Nil | 2026-06-06
21 | June 16-2026 | HENKEL ANAND |  | 280486 | 2026-06-06 |  |  | SHUBHAM SIR | No need to follow up | 147421 received on June 4; Payment will be done this week and PO will be raised
22 | June 16-2026 | LABAT ASIA |  | 206737 | 2026-06-06 | Mr. deepak | 70870 32512 | Ratnesh | Check on Wed; Ledger on Monday | 22374/- 15 MAY & 12743/- 13 MAY; Payment will be done this week | 89k all due
23 | June 16-2026 | MARELLI (INDIA) |  | Nil | 2026-06-06 |  |  | ---------- |  | 45136/- ON 15 MAY; 9211 on May 25 | 45136/- by 11 may |  | To be finalised by Bharat
24 | June 16-2026 | PRG TECH |  | Nil | 2026-06-06
25 | June 16-2026 | SG ENGINEERING |  | 413 | 2026-06-06 |  |  | ---------- | No need to follow up
26 | June 16-2026 | SIMSUN INNOTECH |  | 19790 | 2026-06-06 |  |  | SHUBHAM SIR |  |  | all due
27 | June 16-2026 | SML MAHINDRA |  | Nil | 2026-06-06
28 | June 16-2026 | YASH AIRTECH |  | 52534 | 2026-06-06 | Mr.sanjeev | 82196 06827 | RATNESH | Aruti | 16960 on May 26; payment will be done by end of this week | all due
29 | June 16-2026 | GOEL ENTERPRISES |  | 21240 | 2026-06-06 | Mr. Avdeesh +91 988050826 |  | ---------- | Aruti | Invoice was sent on May 29; Email sent again as per the request of the customer | no due date
30 | June 16-2026 | INDRONES |  | Nil | 2026-06-06 |  |  | ----------
31 | June 16-2026 | PASSIM |  | Nil | 2026-06-06 |  |  | ----------
32 | June 16-2026 | BAAZ BIKES |  | Nil | 2026-06-06 |  |  | ----------
33 | June 16-2026 | UNO MINDA (VTT ENGCON) |  | 303732 | 2026-06-06 | Mr. Manoj | 88021 62267 | ---------- | Aruti; wait till June 25 ( VTT GROUP ) | 2025-06-01
34 | June 16-2026 | EMETEC SOLUTION |  | Nil | 2026-06-06 |  |  | shubham sir
35 | June 16-2026 | AMISON ENGENEERING |  | Nil | 2026-06-06
36 | June 16-2026 | ATOMBERG |  | 23010 | 2026-06-06 | Mr. Vivek patil | 93092 55409 |  | Wait to follow up; Aruti | 23600 received on June 3, 2026; | 2026-06-25
37 | June 16-2026 | sark industries |  | Nil | 2026-06-06 |  |  |  |  | 1770 payment came on May 28
38 | June 16-2026 | RAPID PROTO |  | Nil | 2026-06-06 |  |  | SHUBHAM SIR |  |  | 2026-06-13
39 | June 16-2026 | scope medical |  | 6101 | 2026-06-06 |  |  |  | Shubham needs to follow up
40 | June 16-2026 | Enertics |  | 30007 | 2026-06-06 |  |  | Bharat | Ask Bharat | Invoice was sent on June 5;
41 | June 16-2026 | HC Robotics |  | 133725 | 2026-06-06 |  |  | SHUBHAM SIR | Ask Shubham after 22 June | 335082 on 20 June; 24553 on 21 June; 74090 on 22 June
42 | June 16-2026 | PPI Proto Plasts India |  | 4484 |  |  |  | SHUBHAM SIR | Shubham will follow up | 4484 on March 21 Payment will be done this week
| June 16-2026 | TOTAL |  | 2353308

## 18 june
2026-06-16
SR. | PARTICULARS |  | CLOSING BALANCE DR |  |  |  | HANDLE BY |  | REMARKS on Payment Received | DUE ON | last correspondence on | Payment Terms
NO |  | Due Amount(as of today) | AMOUNT | AS ON | Contact | Phone |  | Follow Up to be Done
1 | AEBOCODE TECHNOLOGIES | 256323 | 262955 | 18-06-2026 |  |  | BHARAT SIR | Bharat needs to be ask for the payment and order also | 3,00,000 on May 22; Message dropped; no response yet
2 | AVEER INDUSTRIES |  | Nil | 18-06-2026 | Mandeep | 90411 89436; 9672610034 Saurabh for payment | SHUBHAM SIR | Payment will be done by end of this week / saurabh did not reply | 3717/- rec on 16 june 2026 | 2026-06-04
3 | BAJAJ ELECTRICALS LIMITED |  | 76945 | 18-06-2026 |  |  | RATNESH |  | DUE ON 16 JULY 2026 76945/-
4 | ENDURAIR SYSTEMS PVT LTD | 76834 | 97634 | 18-06-2026 |  |  | SHUBHAM SIR | Shreeya talked to Ankur payment will be done by today | 1,15,445 received on June 6, 2026 | 65,052 due after May 31; 27824 due on 3 July
5 | GROUP SEB |  | NIl | 18-06-2026
6 | HAVELLS INDIA LIMITED |  | NIl | 18-06-2026
7 | HELLA INDIA | 27122 | 65077 | 18-06-2026 |  |  | BHARAT SIR | Wait till June 26; Shubham will check after that |  | 26 June 2026; As of due 27122
8 | ITL SONALIKA | 179156 | 195156 | 18-06-2026 |  |  | Shubham sir | Payment to come this week pending invoices shared with Ra | 75080/- rec on 17 june
9 | MY DESIGN MINDS | He is in debt | 103642 | 18-06-2026 |  |  | Shubham sir | Wait till June 30 | 50000/- ON 16 MAY | all due
10 | ORIENT ELECTRIC LIMITED |  | 63738 | 18-06-2026 |  |  | Rohit sir | Rohit and Shubham | 19,387 due on June 12; 30,042 due on June 21; 25,879 on July 4 | 7816/- 09 march 2026
11 | ELIN APPLIANCES |  | NIl | 18-06-2026 |  |  |  | Aruti
12 | mobility solution |  | 65161 | 18-06-2026 | Mr. Manu | +91 87250 68321 | shubham sir | Bharat needs to visit | Payment was pending so reports were kept on hold; | all due since April 16
13 | Jal bath |  | Nil | 18-06-2026
14 | kyocera avx |  | Nil | 18-06-2026 | Mr. Nishant | 930466 8342 | SHUBHAM SIR | Aruti | 21421/- rec on 17 june 2026 | 2026-06-07
15 | microtek |  | 5612 | 18-06-2026 |  |  | SHUBHAM SIR | Aruti | 25626/- rec on 17 june 2026 | all due by 11 may
16 | techno plastic |  | Nil | 18-06-2026
17 | NIPA | 16307 | 41782 | 18-06-2026 |  |  | RATNESH | No need to follow up | 4307 received on May 31; 16307 due on June 3; 11351 due on June 11; 22078 due on Jun 18; 3398 due on June 24 | 4307/- 21 may
18 | Modern manufeactures |  | Nil | 18-06-2026 |  |  | -----------
19 | AV MACHINING SOLUTION |  | 419275 | 18-06-2026 |  |  | ROHIT SIR shubham | Aruti; follow up on Tuesday for 2-3 Lakhs | 1,00,000 received on June 6 |  |  | To be finalised by Bharat
20 | DAIKIN AIRCONDITIONING |  | Nil | 18-06-2026
21 | HENKEL ANAND |  | 280486 | 18-06-2026 |  |  | SHUBHAM SIR | No need to follow up | 147421 received on June 4; Payment will be done this week and PO will be raised
22 | LABAT ASIA |  | 171535 | 18-06-2026 | Mr. deepak | 70870 32512 | Ratnesh | Check on Wed; Ledger on Monday | 22374/- 15 MAY & 12743/- 13 MAY; Payment will be done this week | 89k all due
23 | MARELLI (INDIA) |  | Nil | 18-06-2026 |  |  | ---------- |  | 45136/- ON 15 MAY; 9211 on May 25 | 45136/- by 11 may |  | To be finalised by Bharat
24 | PRG TECH |  | Nil | 18-06-2026
25 | SG ENGINEERING |  | 413 | 18-06-2026 |  |  | ---------- | No need to follow up
26 | SIMSUN INNOTECH |  | 19790 | 18-06-2026 |  |  | SHUBHAM SIR |  |  | all due
27 | SML MAHINDRA |  | Nil | 18-06-2026
28 | YASH AIRTECH | 52534 | 52534 | 18-06-2026 | Mr.sanjeev | 82196 06827 | RATNESH | Aruti | 16960 on May 26; payment will be done by end of this week | all due
29 | GOEL ENTERPRISES |  | 42480 | 18-06-2026 | Mr. Avdeesh +91 988050826 |  | ---------- | Aruti | Invoice was sent on May 29; Email sent again as per the request of the customer | no due date
30 | INDRONES |  | Nil | 18-06-2026 |  |  | ----------
31 | PASSIM |  | Nil | 18-06-2026 |  |  | ----------
32 | BAAZ BIKES |  | Nil | 18-06-2026 |  |  | ----------
33 | UNO MINDA (VTT ENGCON) |  | 303732 | 18-06-2026 | Mr. Manoj | 88021 62267 | ---------- | Aruti; wait till June 25 ( VTT GROUP ) | 2025-06-01
34 | EMETEC SOLUTION |  | Nil | 18-06-2026 |  |  | shubham sir
35 | AMISON ENGENEERING |  | Nil | 18-06-2026
36 | ATOMBERG |  | 23010 | 18-06-2026 | Mr. Vivek patil | 93092 55409 |  | Wait to follow up; Aruti | 23600 received on June 3, 2026; | 2026-06-25
37 | sark industries |  | Nil | 18-06-2026 |  |  |  |  | 1770 payment came on May 28
38 | RAPID PROTO |  | Nil | 18-06-2026 |  |  | SHUBHAM SIR |  |  | 2026-06-13
39 | scope medical | 6101 | 6101 | 18-06-2026 |  |  |  | Shubham needs to follow up
40 | Enertics | 47253 | 47253 | 18-06-2026 |  |  | Bharat | Ask Bharat | Invoice was sent on June 5;
41 | HC Robotics | 1770 | 135495 | 18-06-2026 |  |  | SHUBHAM SIR | Ask Shubham after 22 June | 335082 on 20 June; 24553 on 21 June; 74090 on 22 June
42 | PPI Proto Plasts India | 4484 | 4484 | 18-06-2026 |  |  | SHUBHAM SIR | Shubham will follow up | 4484 on March 21 Payment will be done this week
43 | menthosa |  | Nil | 18-06-2026 |  |  |  |  | 25370/- rec on june 2026
44 | PARAM APPLIANCES | 4234 | 4234 | 18-06-2026
45
| TOTAL |  | 2484290